## Sheet1
Vendor | Audit.Status | In.USA.or.OUS | Location | Services.Audited | GxP.Area | Audit.Type | Audit.Method | Proposed.Quarter | VRTX.QA.Coordinator | GxP.Auditor | CSQA.Auditor | TW.Report.Number | Date.of.Intake | Date.Q.sent | Date.Q.Rcvd | Date.On.Site.Scheduled | Audit.Start.Date | Audit.End.Date | Date.Final..Report.Due | Date.of..Completion | Completed | Days_Intake_Qsent | Days_Qsent_Qreceived | Days_OnSiteScheduled_AuditStartDate | Days_StartDate_EndDate | Days_AuditEnd_FinalReportDue | Days_FinalReportDue_CompletionDate
Vendor1 | Not In Scope | OUS | Bonn, Germany | consulting/cenral budget negotiations for sites lcoated in Germany, Vendor (select studies), and website posting (select studies) | GCP | Qualification | None | Q2 | JMD | (Unknown) | (Unknown) | (Unknown) | 2017-01-05 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor2 | Closed | USA | Princeton, NJ | CRO | GCP | Qualification | On Site | Q1 | JMD | MR | DF | 22552 | 2017-01-05 | (Unknown) | (Unknown) | (Unknown) | 2017-02-14 | 2017-02-16 | 2017-03-15 | 2017-03-16 | Delayed | #VALUE! | #VALUE! | #VALUE! | 2 | 27 | -1
Vendor3 | Pending | OUS | Munich, Germany | (Unknown) | GCP | Qualification | TBD | Q3 | JMD | (Unknown) | (Unknown) | (Unknown) | 2017-01-05 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor4 | Completed | USA | Indianapolis, IN | Life cycle of data during the sample processing stages; Study start up; Translation of protocols into lab tests and how they are performed, documented, and managed; Global processes and harmonization between other Vendor sites; Linkage of systems at other Vendor labs and usage of a centralized system for data; Robust process in place for third party labs and oversight of transferring samples at different locations; Tech transfer process; Sample management | GCP | Qualification | On Site | Q1 | JMD | MR | AA | (Unknown) | 2017-01-05 | (Unknown) | (Unknown) | 2017-06-05 | 2017-07-12 | 2017-07-13 | 2017-08-12 | 2017-08-11 | On-time | #VALUE! | #VALUE! | 37 | 1 | 30 | 1
Vendor5 | Closed | OUS | Heidelberg, Germany | (Unknown) | GCP | Qualification | On Site | Q1 | JMD | PK | DF | 22501 | 2017-01-13 | (Unknown) | (Unknown) | (Unknown) | 2017-02-07 | 2017-02-08 | 2017-03-10 | 2017-03-10 | On-time | #VALUE! | #VALUE! | #VALUE! | 1 | 30 | 0
Vendor6 | Closed | OUS | Ontaria, Canada | Registry Database | GCP | Qualification | Questionnaire | Q1 | JMD | JO | LG | 22620 | 2017-01-13 | 2017-01-19 | 2017-02-01 | (Unknown) | (Unknown) | (Unknown) | 2017-03-03 | 2017-03-03 | On-time | 6 | 13 | #VALUE! | #VALUE! | #VALUE! | 0
Vendor7 | Closed | OUS | Oakville, Canada | (Unknown) | GCP | Qualification | Questionnaire | Q1 | JMD | JO | LG | 22372 | 2017-01-13 | 2017-01-19 | 2017-02-02 | (Unknown) | (Unknown) | (Unknown) | 2017-03-03 | 2017-03-03 | On-time | 6 | 14 | #VALUE! | #VALUE! | #VALUE! | 0
Vendor8 | Closed | USA | Durham, NC | (Unknown) | GCP | Requalification | On Site | Q1 | JMD | KB | MD | 23134 | 2017-01-13 | (Unknown) | (Unknown) | 2017-01-13 | 2017-02-20 | 2017-02-23 | 2017-03-25 | 2017-03-24 | On-time | #VALUE! | #VALUE! | 38 | 3 | 30 | 1
Vendor9 | Closed | USA | Mattawan, MI | General Toxicology Genetic Toxicology Carcinogenicity Safety Pharmacology Analytical Bioanalytical Toxicokinetics | GLP | Requalification | On Site | Q2 | MM | RD | AK | 23135 | 2017-01-13 | (Unknown) | (Unknown) | 2017-03-17 | 2017-04-25 | 2017-04-27 | 2017-05-27 | 2017-05-19 | On-time | #VALUE! | #VALUE! | 39 | 2 | 30 | 8
Vendor10 | Closed | USA | Rockville, MD | Genetic Toxicology Mammalian Toxicology Clinical Pathology Safety Pharmacology Histopathology Bioanalytical Analytical Toxicokinetics | GLP | Requalification | On Site | Q1 | MM | RD | DF | 22648 | 2017-01-13 | (Unknown) | (Unknown) | 2017-03-08 | 2017-03-21 | 2017-03-23 | 2017-04-22 | 2017-04-21 | On-time | #VALUE! | #VALUE! | 13 | 2 | 30 | 1
Vendor11 | Not In Scope | USA | Ashland, OH | General Toxicology Genetic Toxicology Carcinogenicity Safety Pharmacology Analytical Bioanalytical | GLP | Requalification | None | Q1 | MM | (Unknown) | TBD | (Unknown) | 2017-01-13 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor12 | Closed | USA | Emeryville, CA | (Unknown) | GVP | Qualification | Questionnaire | Q1 | DL | (Unknown) | LG | 22379 | 2017-01-25 | 2017-01-26 | 2017-03-23 | (Unknown) | (Unknown) | (Unknown) | 2017-04-22 | 2017-04-10 | On-time | 1 | 56 | #VALUE! | #VALUE! | #VALUE! | 12
Vendor13 | Closed | OUS | Prague, Czech Republic | (Unknown) | GVP | Qualification | Questionnaire | Q1 | DL | (Unknown) | LG | 22192 | 2017-01-25 | 2017-01-26 | 2017-03-01 | (Unknown) | (Unknown) | (Unknown) | 2017-04-01 | 2017-04-04 | Delayed | 1 | 34 | #VALUE! | #VALUE! | #VALUE! | -3
Vendor14 | Closed | OUS | Petach Tikva, Israel | (Unknown) | GVP | Qualification | Questionnaire | Q1 | DL | (Unknown) | LG | 22203 | 2017-01-25 | 2017-01-27 | 2017-02-28 | (Unknown) | (Unknown) | (Unknown) | 2017-03-30 | 2017-04-04 | Delayed | 2 | 32 | #VALUE! | #VALUE! | #VALUE! | -5
Vendor15 | Closed | OUS | Richmond, United Kingdom | (Unknown) | GVP | Qualification | Questionnaire | Q1 | DL | (Unknown) | LG | 22381 | 2017-01-25 | 2017-01-26 | 2017-03-02 | (Unknown) | (Unknown) | (Unknown) | 2017-04-01 | 2017-04-10 | Delayed | 1 | 35 | #VALUE! | #VALUE! | #VALUE! | -9
Vendor16 | Closed | OUS | Chandigah, India | (Unknown) | GVP | Qualification | Questionnaire | Q1 | DL | (Unknown) | LG | 22223 | 2017-01-25 | 2017-01-26 | 2017-03-08 | (Unknown) | (Unknown) | (Unknown) | 2017-04-07 | 2017-03-23 | On-time | 1 | 41 | #VALUE! | #VALUE! | #VALUE! | 15
Vendor17 | Closed | OUS | Auckland, New Zealand | (Unknown) | GVP | Qualification | Questionnaire | Q1 | DL | (Unknown) | LG | 22380 | 2017-01-25 | 2017-01-26 | 2017-03-08 | (Unknown) | (Unknown) | (Unknown) | 2017-04-07 | 2017-04-27 | Delayed | 1 | 41 | #VALUE! | #VALUE! | #VALUE! | -20
Vendor18 | Not In Scope | OUS | Vincenza, Italy | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution, Test Articles, Reference Standard | GMP | Requalification | None | Q1 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | 2017-02-07 | 2017-02-21 | 2017-02-24 | 2017-03-26 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 14 | 3 | 30 | #VALUE!
Vendor19 | Not In Scope | OUS | Ponte Cremenaga, Swizerland | Spray Dried Dispersion Dry Powder Inhaler Characterization | GMP | Qualification | None | Q1 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor20 | In Progress | OUS | Dudley, United Kingdom | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution, Test Articles, Reference Standard | GMP | Requalification | On Site | Q1 | GN | TB | TB | 21871 | 2017-02-08 | (Unknown) | (Unknown) | 2017-05-04 | 2017-05-10 | 2017-05-10 | 2017-06-09 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 6 | 0 | 30 | #VALUE!
Vendor21 | In Progress | USA | Malvern, PA | DS Intermediate and/or DS Mfg., Analytical Services, Warehouse & Distribution, Test Articles, Reference Standard | GMP | Requalification | On Site | Q1 | GN | RN | DF | 21875 | 2017-02-08 | (Unknown) | (Unknown) | 2017-05-04 | 2017-06-12 | 2017-06-13 | 2017-07-13 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 39 | 1 | 30 | #VALUE!
Vendor22 | Completed | USA | Bensenville, IL | Warehouse & Distribution, Brokerage / Transportation | GDP | Qualification | On Site | Q1 | GN | LDS | CR | 21876 | 2017-02-08 | (Unknown) | (Unknown) | Week of 20 Feb | 2017-02-20 | 2017-02-21 | 2017-03-23 | 2017-03-23 | On-time | #VALUE! | #VALUE! | #VALUE! | 1 | 30 | 0
Vendor23 | Completed | USA | High Point, NC | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution; Test Articles, Reference Standard | GMP | Requalification | On Site | Q2 | GN | LDS | DF | 21879 | 2017-02-08 | (Unknown) | (Unknown) | 2017-03-24 | 2017-04-03 | 2017-04-04 | 2017-05-04 | 2017-05-04 | On-time | #VALUE! | #VALUE! | 10 | 1 | 30 | 0
Vendor24 | In Progress | USA | Charles City, IA | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Qualification | On Site | Q2 | GN | LDS | AA | 21880 | 2017-02-08 | 2017-04-20 | (Unknown) | 2017-05-04 | 2017-06-20 | 2017-06-21 | 2017-07-21 | (Unknown) | (Unknown) | 71 | #VALUE! | 47 | 1 | 30 | #VALUE!
Vendor25 | In Progress | OUS | Tokyo, Japan | Raw Material Mfg., Starting Matertial Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Qualification | On Site | Q2 | GN | TB | TB | 22033 | 2017-02-08 | (Unknown) | (Unknown) | 2017-05-04 | 2017-06-26 | 2017-06-27 | 2017-07-27 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 53 | 1 | 30 | #VALUE!
Vendor26 | Pending | OUS | Jiuzhou, China | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Qualification | On Site | Q2 | GN | TB | TB | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor27 | Pending | OUS | Goa, India | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Qualification | On Site | Q2 | GN | TB | TB | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor28 | Not In Scope | USA | Secaucus, NJ | Comparator/co-medication purchase; ability to outsource placebo development and manufacturing to a third party | GMP | Qualification | None | Q2 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor29 | Not In Scope | OUS | Brampton, Canada | Warehouse & Distribution | GDP | Requalification | Q in 2016 | Q2 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor30 | Not In Scope | OUS | Ankara, Turkey | Warehouse & Distribution | GDP | Qualification | None | Q2 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor31 | Not In Scope | OUS | Harsewinkel, Germany | Warehouse & Distribution | GDP | Qualification | None | Q2 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor32 | Not In Scope | OUS | Moscow, Russia | Warehouse & Distribution | GDP | Qualification | None | Q2 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor33 | In Progress | USA | Whippany, NJ | DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Requalification | On Site | Q2 | GN | SK | JR | 21870 | 2017-02-08 | (Unknown) | (Unknown) | 2017-05-03 | 2017-05-31 | 2017-06-01 | 2017-07-01 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 28 | 1 | 30 | #VALUE!
Vendor34 | Scheduled | USA | Wilmington, NC | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Requalification | On Site | Q2 | GN | (Unknown) | CL | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | 2017-06-30 | 2017-10-10 | 2017-10-11 | 2017-11-10 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 102 | 1 | 30 | #VALUE!
Vendor35 | Scheduled | OUS | Jiande Zhejiang, China | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution, Test Articles, Reference Standard | GMP | Requalification | On Site | Q2 | GN | SK | AK | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | 2017-09-27 | 2017-11-27 | 2017-11-28 | 2017-12-28 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 61 | 1 | 30 | #VALUE!
Vendor36 | In Progress | USA | Lancaster, PA | Analytical Services, Microbiology Testing Services | GMP | Requalification | On Site | Q2 | GN | RJC | BM | 21888 | 2017-02-08 | (Unknown) | (Unknown) | 2017-08-03 | 2017-08-31 | 2017-08-31 | 2017-09-30 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 28 | 0 | 30 | #VALUE!
Vendor37 | Scheduled | USA | Rockford, IL | Pkg. & Labeling Mfg., Analytical Services, Warehouse & Distribution | GDP | Requalification | On Site | Q2 | GN | CT | PW | 21889 | 2017-02-08 | (Unknown) | (Unknown) | 2017-09-20 | 2017-10-12 | 2017-10-13 | 2017-11-12 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 22 | 1 | 30 | #VALUE!
Vendor38 | In Progress | OUS | Deajeon, Korea | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Requalification | On Site | Q2 | GN | TB | TB | 21890 | 2017-02-08 | (Unknown) | (Unknown) | 2017-05-04 | 2017-06-29 | 2017-06-30 | 2017-07-30 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 56 | 1 | 30 | #VALUE!
Vendor39 | In Progress | OUS | Loures, Portugal | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution, Test Articles | GMP | Requalification | On Site | Q2 | GN | (Unknown) | WS | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | 2017-05-04 | 2017-09-27 | 2017-09-29 | 2017-10-29 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 146 | 2 | 30 | #VALUE!
Vendor40 | In Progress | USA | Bend, OR | Starting Matertial Mfg., DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution, Test Articles, Reference Standard | GMP | Requalification | On Site | Q2 | GN | (Unknown) | WS | 21892 | 2017-02-08 | (Unknown) | (Unknown) | 2017-05-02 | 2017-08-01 | 2017-08-02 | 2017-09-01 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 91 | 1 | 30 | #VALUE!
Vendor41 | Not In Scope | USA | Highland Park, NJ | 503a Compounding Services | GMP | Requalification | None | Q2 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor42 | In Progress | OUS | Dartford, United Kingdom | DS Intermediate and/or DS Mfg., Analytical Services, Warehouse & Distribution, Test Articles, Reference Standard | GMP | Requalification | On Site | Q3 | GN | TB | TB | 21897 | 2017-02-08 | (Unknown) | (Unknown) | 2017-05-04 | 2017-07-10 | 2017-07-10 | 2017-08-09 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 67 | 0 | 30 | #VALUE!
Vendor43 | In Progress | OUS | Courroux, Switzerland | Starting Matertial Mfg., DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Requalification | On Site | Q3 | GN | SK | AA | 21900 | 2017-02-08 | (Unknown) | (Unknown) | 2017-06-30 | 2017-09-18 | 2017-09-19 | 2017-10-19 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 80 | 1 | 30 | #VALUE!
Vendor44 | In Progress | OUS | Latina, ltaly | Starting Matertial Mfg., DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Requalification | On Site | Q3 | GN | JR | ES | 21901 | 2017-02-08 | (Unknown) | (Unknown) | 2017-06-30 | 2017-09-21 | 2017-09-22 | 2017-10-22 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 83 | 1 | 30 | #VALUE!
Vendor45 | Cancelled | USA | Knoxville, TN | Analytical Services | GMP | Requalification | None | Q3 | GN | EZ | PW | 21902 | 2017-02-08 | (Unknown) | (Unknown) | 2017-06-26 | 2017-09-19 | 2017-09-19 | 2017-10-19 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 85 | 0 | 30 | #VALUE!
Vendor46 | Pending | USA | Brooks, KY | Pkg. & Labeling Mfg., Warehouse & Distribution | GMP/GDP | Requalification | On Site | Q4 | GN | Vendor3 | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor47 | Pending | USA | Reno, NV | Pkg. & Labeling Mfg., Warehouse & Distribution | GMP/GDP | Requalification | On Site | Q4 | GN | Vendor3 | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor48 | Scheduled | USA | Horsham, PA | DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Requalification | On Site | Q4 | GN | (Unknown) | WS | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | 2017-09-14 | 2017-10-24 | 2017-10-25 | 2017-11-24 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 40 | 1 | 30 | #VALUE!
Vendor49 | Pending | OUS | Rydalmere, Australia | Warehouse & Distribution | GDP | Requalification | Questionnaire | Q4 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor50 | Cancelled | USA | Somerset, NJ | Starting Matertial Mfg., DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Requalification | None | Q4 | GN | RN | BM | 21907 | 2017-02-08 | (Unknown) | (Unknown) | 2017-08-03 | 2017-09-19 | 2017-09-20 | 2017-10-20 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 47 | 1 | 30 | #VALUE!
Vendor51 | Pending | OUS | Visp, Switzerland | Raw Material Mfg., Starting Material Mfg., DS Intermediate and/or DS Mfg., DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution and Cell Bank Storage | GMP | Requalification | On Site | Q4 | GN | (Unknown) | TB | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor52 | In Progress | USA | Columbia, SC | Starting Matertial Mfg., DP Intermediate and/or DP Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Requalification | On Site | Q4 | GN | (Unknown) | DF | 21911 | 2017-02-08 | (Unknown) | (Unknown) | 2017-08-03 | 2017-09-26 | 2017-09-27 | 2017-10-27 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 54 | 1 | 30 | #VALUE!
Vendor53 | Not In Scope | OUS | Starnberg, Germany | Device Mfg. | GMP | Qualification | (Unknown) | Q4 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor54 | Not In Scope | USA | Midlothian, VA | Device Mfg. | GMP | Qualification | (Unknown) | Q4 | GN | (Unknown) | (Unknown) | (Unknown) | 2017-02-08 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor55 | Closed | USA | Mason, OH | Pathology services | GLP | Qualification | On Site | Q1 | MM | RD | CL | 23131 | 2017-02-09 | 2017-05-08 | 2017-05-19 | 2017-03-31 | 2017-05-24 | 2017-05-24 | 2017-06-23 | 2017-06-23 | On-time | 88 | 11 | 54 | 0 | 30 | 0
Vendor56 | Not In Scope | USA | Lenexa, KS | Bioanalytical | GLP | Requalification | None | Q1 | MM | (Unknown) | (Unknown) | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor57 | Not In Scope | OUS | Montreal, Canada | Genetal Toxicology Drug Metabolism Toxicokinetics | GLP | Requalification | None | Q2 | MM | (Unknown) | (Unknown) | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor58 | Not In Scope | OUS | Quebec City, Canada | Toxicokinetics | GLP | Requalification | None | Q2 | MM | (Unknown) | (Unknown) | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor59 | In Progress | OUS | Assen, New Zealand | Bioanalytical | GLP | Requalification/Q | On Site | Q2 | MM | OG | AK | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | 2017-06-29 | 2017-09-19 | 2017-09-21 | 2017-10-21 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 82 | 2 | 30 | #VALUE!
Vendor60 | Scheduled | USA | Sterling, VA | Archival Services | GLP | Requalification | On Site | Q3 | MM | RD | AA | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | 2017-06-16 | 2017-11-15 | 2017-11-16 | 2017-12-16 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 152 | 1 | 30 | #VALUE!
Vendor61 | Scheduled | USA | Sterling, VA | Pathology services | GLP | Requalification | On Site | Q3 | MM | (Unknown) | AA | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | 2017-06-16 | 2017-11-14 | 2017-11-14 | 2017-12-14 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 151 | 0 | 30 | #VALUE!
Vendor62 | Scheduled | USA | Middleton, WI | Bioanalytical | GLP | Requalification | On Site | Q3 | MM | RD | CL | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | 2017-06-29 | 2017-11-29 | 2017-12-01 | 2017-12-31 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 153 | 2 | 30 | #VALUE!
Vendor63 | Scheduled | USA | Ithaca, NY | Bioanalytical | GLP | Requalification/Q | On Site | Q4 | MM | (Unknown) | BM | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | 2017-09-15 | 2017-11-14 | 2017-11-15 | 2017-12-15 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 60 | 1 | 30 | #VALUE!
Vendor64 | In Progress | USA | East Millstone, NJ | Toxicokinetics Bioanalysis General Toxicology Inhalation Analytical Carcinogenicity Safety Pharmacology Reproductive Toxicology | GLP | Requalification/Q | On Site | Q4 | MM | MM and KD | AA | (Unknown) | 2017-02-09 | (Unknown) | (Unknown) | 2017-08-31 | 2017-10-03 | 2017-10-05 | 2017-11-04 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 33 | 2 | 30 | #VALUE!
Vendor65 | Closed | USA | Salt Lake City, UT | Data Transfer, Activity Testing & Sequencing Assay | GCP | Qualification | On Site | Q1 | JMD | MR | DF | 23141 | 2017-02-24 | (Unknown) | (Unknown) | 2017-03-17 | 2017-04-19 | 2017-04-20 | 2017-05-20 | 2017-05-19 | On-time | #VALUE! | #VALUE! | 33 | 1 | 30 | 1
Vendor66 | Closed | USA | Valencia, CA San Jaun Capistrano, CA | Antigen Receptor Assay, Data transfer and Sample Receipt/management, and expiry | GCP | Requalification | On Site | Q2 | JMD | JM | DF | 23237 | 2017-04-14 | (Unknown) | (Unknown) | 2017-04-14 | 2017-05-23 | 2017-05-24 | 2017-06-23 | 2017-06-22 | On-time | #VALUE! | #VALUE! | 39 | 1 | 30 | 1
Vendor67 | Not In Scope | USA | Baltimore, MD | Biopsy Sample Kits & Sample Analysis | GLP | Qualification | On Site | Q2 | MM | MR | see notes | (Unknown) | 2017-04-14 | (Unknown) | (Unknown) | 2017-04-14 | 2017-05-01 | 2017-05-02 | 2017-06-01 | 2017-05-25 | On-time | #VALUE! | #VALUE! | 17 | 1 | 30 | 7
Vendor68 | In Progress | OUS | Neuland, Switzerland | Raw Material Mfg., Starting Matertial Mfg., DS Intermediate and/or DS Mfg., Analytical Services, Microbiology Services, Stability Testing Services, Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Qualification | Questionnaire | Q2 | GN | JR | WS | 22664 | 2017-04-21 | 2017-05-04 | 2017-05-19 | 2017-05-04 | 2017-05-24 | 2017-05-24 | 2017-06-23 | (Unknown) | (Unknown) | 13 | 15 | 20 | 0 | 30 | #VALUE!
Vendor69 | Closed | OUS | Groningen, New Zealand | SDTM | GCP | Requalification | Remote | Q1 | JMD | SK | AK | 23178 | 2017-03-08 | (Unknown) | (Unknown) | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-04-05 | 2017-04-05 | On-time | #VALUE! | #VALUE! | 0 | 0 | 30 | 0
Vendor70 | Not In Scope | OUS | Sydney, Australia | (Unknown) | GCP | (Unknown) | (Unknown) | (Unknown) | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor71 | Not In Scope | USA | Columbia, MD | (Unknown) | GCP | (Unknown) | (Unknown) | (Unknown) | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor72 | Not In Scope | OUS | Paris, France | (Unknown) | GCP | (Unknown) | None | (Unknown) | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor73 | Not In Scope | OUS | Dublin, Ireland | (Unknown) | GCP | (Unknown) | None | (Unknown) | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor74 | Pending | USA | Cincinati, OH | (Unknown) | GCP | (Unknown) | TBD | (Unknown) | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor75 | Not In Scope | USA | Madison, WI | Phase 1 Clinical Research Unit | GCP | Requalification | None | Q3 | MJ | MJ | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | 2017-07-11 | 2017-07-13 | 2017-08-12 | 2017-08-16 | Delayed | #VALUE! | #VALUE! | #VALUE! | 2 | 30 | -4
Vendor76 | Closed | USA | Bluebell, PA | Model | GCP | Requalification | On Site | Q3 | JMD | MS | BM | (Unknown) | (Unknown) | (Unknown) | (Unknown) | 2017-07-18 | 2017-08-09 | 2017-08-10 | 2017-09-09 | 2017-09-07 | On-time | #VALUE! | #VALUE! | 22 | 1 | 30 | 2
Vendor77 | Cancelled | USA | Moorestown, NJ | Packaging & Labeling Mfg., Warehouse & Distribution | GMP | Qualification | None | Q3 | GN | (Unknown) | BM | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor78 | Completed | OUS | Kaiseraugst, Switzerland | Method setup, method validation/co-validation, and method transfer, analytical testing for release and stability - for DP & DS | GMP | Qualification | On Site | Q3 | GN | ZP | DF | 23615 | (Unknown) | (Unknown) | (Unknown) | 2017-06-30 | 2017-08-08 | 2017-08-09 | 2017-09-08 | 2017-09-08 | On-time | #VALUE! | #VALUE! | 39 | 1 | 30 | 0
Vendor79 | Closed | USA | Princeton, NJ | electronic systems | GCP | Requalification | Remote | Q3 | MJ | (Unknown) | DF | 23605 | (Unknown) | (Unknown) | (Unknown) | 2017-08-02 | 2017-08-22 | 2017-08-23 | 2017-09-22 | 2017-09-25 | Delayed | #VALUE! | #VALUE! | 20 | 1 | 30 | -3
Vendor80 | Pending | OUS | Nottingham, United Kingdom | (Unknown) | GCP | Qualification | On Site | Q3 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor81 | Not In Scope | USA | Raliegh,NC | (Unknown) | GCP | Qualification | None | Q3 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor82 | In Progress | OUS | Lisbon, Portugal | Warehouse & Distribution | GMP | Qualification | On Site | Q3 | GN | Vendor3 | WS | (Unknown) | 2017-08-03 | (Unknown) | (Unknown) | 2017-09-08 | 2017-09-25 | 2017-09-26 | 2017-10-26 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 17 | 1 | 30 | #VALUE!
Vendor83 | Not In Scope | USA | Cambridge, MA | (Unknown) | GCP | Qualification | None | Q3 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor84 | Not In Scope | USA | Durham, NC | (Unknown) | GCP | Requalification | None | Q3 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor85 | Not In Scope | USA | Woburn, MA | (Unknown) | GCP | Qualification | None | Q3 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor86 | Scheduled | USA | Rochester, NY | Services for clinical trials, Project Management, Core Lab Services, Equipment Management | GCP | Requalification | On Site | Q3 - Q4 | JMD | KC | TBD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | 2017-09-07 | 2017-11-01 | 2017-11-02 | 2017-12-02 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 55 | 1 | 30 | #VALUE!
Vendor87 | Pending | USA | Bethesda MD | (Unknown) | GCP | Requalification | On Site | Q3 - Q4 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor88 | Scheduled | OUS | Fibtaine-les-Dijon, France | (Unknown) | GCP | Requalification | On Site | Q3 - Q4 | JMD | CH | TBD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | 2017-09-07 | 2017-11-13 | 2017-11-14 | 2017-12-14 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 67 | 1 | 30 | #VALUE!
Vendor89 | Pending | OUS | North Wales, Australia | (Unknown) | GCP | Requalification | On Site | Q4 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor90 | Pending | USA | Los Angeles, CA | (Unknown) | GCP | Requalification | On Site | Q4 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor91 | Pending | OUS | Singapore, Singapore | (Unknown) | GCP | Requalification | On Site | Q4 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor92 | Pending | OUS | Dublin, Ireland | (Unknown) | GCP | Requalification | On Site | Q4 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor93 | Not In Scope | USA | Puyallup, WA | (Unknown) | GCP | Requalification | None | Q4 | JMD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vendor94 | In Progress | USA | Middleton, WI | Analytical Services & Stability Testing Services for clinical and commercial (GMP) | GMP | Qualification | On Site | Q4 | GN | RN | PW | 23616 | (Unknown) | (Unknown) | (Unknown) | (Unknown) | 2017-08-31 | 2017-08-31 | 2017-09-30 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | #VALUE! | 0 | 30 | #VALUE!
Vendor95 | Scheduled | OUS | Leiden, Netherlands | Serve as CRU for phase 1 Study | GCP | Qualification | On Site | Q3 | MJ | (Unknown) | SK | (Unknown) | (Unknown) | (Unknown) | (Unknown) | 2017-08-21 | 2017-11-13 | 2017-11-14 | 2017-12-14 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 84 | 1 | 30 | #VALUE!
Vendor96 | Cancelled | USA | NJ/Los Angeles (Unknown) | (Unknown) | GCP | Requalification | None | Q3 | JMD | MS | TBD | (Unknown) | (Unknown) | (Unknown) | (Unknown) | 2017-09-07 | 2017-11-14 | 2017-11-15 | 2017-12-15 | (Unknown) | (Unknown) | #VALUE! | #VALUE! | 68 | 1 | 30 | #VALUE!
[21 empty] | Mean | 17.3636 | 29.2 | 54.4889 | 1.06 | 29.94 | 0.16
[21 empty] | Median | 2 | 33 | 47 | 1 | 30 | 0
In/Out USA | Frequency | Percentage
USA | 51 | 53.12%
OUS | 45 | 46.88%
Total | 96 | 100%
GxP.Area | Frequecy | Percentage
GCP | 34 | 35.42%
GLP | 14 | 14.58%
GVP | 6 | 6.25%
GMP | 33 | 34.38%
GDP | 7 | 7.292%
GMP/GDP | 2 | 2.083%
GMP | 0 | 0%
GLP | 0 | 0%
Total | 96 | 100%
Audit.Type | Frequency | Percentage
Qualification | 38 | 39.58%
Requalification | 50 | 52.08%
Requalification/Q | 3 | 3.125%
(Unknown) | 5 | 5.208%
Requalification | 0 | 0%
Total | 96 | 100%
Audit.Method | Frequency | Percentage | [21 empty] | Days_OnSiteScheduled_AuditStartDate
None | 24 | 25%
On Site | 53 | 55.21%
TBD | 2 | 2.083%
Questionnaire | 10 | 10.42%
Q in 2016 | 1 | 1.042%
(Unknown) | 4 | 4.167%
Remote | 2 | 2.083%
Total | 96 | 100%
Audit.Status | Frequency | Percentages
Not In Scope | 26 | 27.08%
Closed | 19 | 19.79%
Pending | 14 | 14.58%
Completed | 4 | 4.167%
In Progress | 18 | 18.75%
Scheduled | 11 | 11.46%
Cancelled | 4 | 4.167%
Total | 96 | 100%
Proposed.Quarter | Frequency | Percentage
Q2 | 27 | 28.12%
Q1 | 23 | 23.96%
Q3 | 21 | 21.88%
Q4 | 17 | 17.71%
(Unknown) | 5 | 5.208%
Q3 - Q4 | 3 | 3.125%
Total | 96 | 100%